PROOF OF CONCEPT PLAN

DataWalk and Hyperscience on Oracle Cloud Infrastructure

Oracle Kubernetes Engine | OCI Government Cloud | SCCA-aligned landing zone

| Document | Value |
| --- | --- |
| Purpose | Authorize and execute a controlled POC, then support a cloud-versus-on-premises decision |
| Frameworks | OCI Cloud Adoption Framework and OCI Well-Architected Framework |
| POC footprint | DataWalk Dev-equivalent cluster + Hyperscience Dev-equivalent cluster |
| Target topology | Five dedicated clusters: DW Dev/Test/Prod and HS Dev/Prod |
| Status | Draft for leadership, security, Oracle, and vendor validation |
| Date | September 3, 2026 |

DECISION REQUESTED Approve prerequisite activities and a controlled non-production POC. Do not authorize production procurement or migration until the version matrix, vendor support statements, performance results, security evidence, operating model, and complete cost model are accepted.

Framework basis. Oracle's Cloud Adoption Framework aligns business strategy, people, security, process, technology, and operations [S1]. Oracle's Well-Architected Framework evaluates the resulting design against five OCI pillars [S2]. This plan uses both: CAF governs how the POC is adopted; WAF governs how the POC is designed and tested.

# 1. Executive recommendation

Proceed with the POC, but treat it as an evidence-producing decision project rather than a small production deployment. The POC should prove that each vendor-supported application can run in its own private OCI Kubernetes environment, meet agreed workload outcomes, integrate through approved storage interfaces, satisfy security controls, and be operated by the assigned teams.

- Use two isolated non-production clusters during the POC: one DataWalk Dev-equivalent cluster and one Hyperscience Dev-equivalent cluster.

- Retain the five-cluster target architecture only as the scale-out pattern after the POC: DW Dev, DW Test, DW Prod, HS Dev, and HS Prod.

- Keep DataWalk on CPU workers unless DataWalk gives written confirmation of a supported GPU-consuming component.

- Use VM.GPU.A10.2 only for confirmed Hyperscience trainer or ORCA workloads. Its two 24 GB A10 GPUs are discrete devices, not one 48 GB memory pool.

- Use FastConnect/DRG and the approved enterprise jump-host path for normal administration. OCI Bastion is optional, not a required traffic component.

- Measure actual utilization and workload results before sizing production. Oracle recommends metrics-driven sizing instead of copying on-premises allocations [S2].

CURRENT ARCHITECTURE DECISION DataWalk and Hyperscience do not share OKE clusters, worker nodes, ingress, databases, storage, application identities, secrets, or upgrade lifecycles. DataWalk Dev and Test are also separate clusters.

# 2. Business outcome and decision questions

The POC supports a final recommendation to leadership on whether OCI is a supportable, secure, performant, and financially responsible target for the next DataWalk and Hyperscience platform generations.

| Decision question | Evidence required |
| --- | --- |
| Vendor supportability | Written matrix for application, Kubernetes, node image/OS, driver, CUDA, database, storage, registry, and ingress versions |
| Functional fit | Representative DataWalk and Hyperscience workflows complete without unsupported workarounds |
| Performance | Agreed workload throughput, latency, accuracy, concurrency, and utilization compared with the current reference |
| Security and ATO readiness | Private topology, least privilege, encryption, logging, vulnerability evidence, egress control, and documented exceptions |
| Reliability | Pod restart, node maintenance/loss, backup, restore, and recovery results against approved RPO/RTO targets |
| Operability | Named ownership, monitoring, patching, upgrade, rollback, incident, vendor-escalation, and evidence-retention procedures |
| Affordability | Measured POC consumption, production run-rate model, licensing, support labor, and five-year TCO with assumptions |

# 3. Scope, exclusions, and assumptions

## 3.1 In scope

- Landing-zone readiness review for compartments, identity, network, security, monitoring, governance, quotas, and budgets.

- Two private OKE clusters with dedicated control planes and worker lifecycles: DataWalk POC and Hyperscience POC.

- DataWalk CPU system/application node pools and required external database or Decoupled Storage services, subject to vendor design.

- Hyperscience CPU platform node pool plus a VM.GPU.A10.2 trainer/application node pool for the approved use case.

- OCI Container Registry, Vault, Monitoring, Logging, Audit, Events/Notifications, approved load balancing, persistent storage, and backup integration.

- Controlled Hyperscience-output-to-DataWalk-ingestion test using OCI Object Storage's S3-compatible interface only if both vendors approve it.

- Functional, performance, security, resilience, operational, and cost testing with retained evidence.

## 3.2 Out of scope

- Production migration, final cutover, production ATO, or decommissioning the current on-premises environments.

- Provisioning all five target clusters before POC approval.

- Claiming DataWalk GPU acceleration without a vendor-supported use case and version matrix.

- Treating the preliminary $663,000 five-year GPU estimate as the complete solution TCO.

- Changing application business workflows beyond what is required to prove platform compatibility and integration.

## 3.3 Governing assumptions

| Assumption | POC treatment |
| --- | --- |
| OCI Government Cloud, target region and availability domain | Confirm current A10.2 capacity, service limits, quotas, and procurement terms before build |
| Existing SCCA landing zone | Reuse approved identity, network, logging, and security guardrails; assess gaps instead of rebuilding the tenancy |
| Private administration | Route through FastConnect/DRG and the approved Windows jump host; no public worker IPs |
| Managed OKE preferred | Proceed only after vendors approve the exact OKE image/OS and Kubernetes version; otherwise evaluate self-managed Kubernetes as a separate decision |
| RHEL 8.10 | DataWalk publicly names RHEL 8.10 or Rocky 8 for its container transition [S10], but this is not proof that managed OKE Oracle Linux workers are vendor-supported |
| Kubernetes SME | Required for design, implementation, operations handoff, troubleshooting, and knowledge transfer |

# 4. POC footprint and target-state relationship

| Layer | POC execution | Post-POC target pattern |
| --- | --- | --- |
| DataWalk | One Dev-equivalent OKE cluster on CPU workers | Separate DW Dev, DW Test, and DW Prod clusters |
| Hyperscience | One Dev-equivalent OKE cluster with CPU platform and A10 GPU pool | Separate HS Dev and HS Prod clusters |
| Ingress | Private endpoint per POC cluster | Dedicated private endpoint per environment |
| State | Dedicated POC DB/storage | Environment-specific DB, storage, keys, backups, retention |
| Identity | Environment-specific service accounts and secrets | No production/non-production trust or credential reuse |
| Operations | POC runbooks and alerts | Approved production SLOs, on-call, patch, backup, DR, and escalation model |

WHY TWO POC CLUSTERS The purpose is to validate each application's required cluster pattern and the integration between them without paying for all five target environments before leadership has the evidence to approve implementation.

## 4.1 Promotion rules after a successful POC

- Rebuild each approved target environment from controlled infrastructure-as-code; do not convert the POC cluster into production.

- Do not promote POC credentials, keys, temporary accounts, unapproved images, or test data into production.

- Apply the signed version matrix and approved configuration baseline separately to DW Dev, DW Test, DW Prod, HS Dev, and HS Prod.

- Require an environment readiness gate before every deployment, including capacity, security, backup, monitoring, support, and cost approval.

- Size production high availability and GPU resiliency from POC evidence and vendor guidance, not from the minimum POC footprint.

5. Approved target architecture pattern

Five dedicated OKE clusters; the POC provisions only the DW Dev-equivalent and HS Dev-equivalent patterns.

Figure 1. Production and non-production cluster boundaries. Node counts and shapes remain subject to vendor sizing and POC evidence.

# 6. OCI Cloud Adoption Framework execution plan

Oracle's CAF uses six pillars to connect business strategy with people, process, security, technology, and operations [S1]. For this POC, each pillar produces an approval artifact rather than a general discussion.

| CAF pillar | POC application | Required evidence / owner |
| --- | --- | --- |
| Business strategy | Define decision, expected mission value, alternatives, cost ceiling, and production trigger | Approved POC charter and decision scorecard / Program leadership |
| People strategy | Establish sponsor, PM, OCI architect, Kubernetes SME, application SMEs, security, network, and operations roles | RACI, training plan, support contacts / PM |
| Security | Apply SCCA guardrails, least privilege, private access, encryption, logging, vulnerability management, and evidence retention | Security control mapping and findings / Security and ATO leads |
| Process design | Define change, release, incident, access, backup, restore, vendor escalation, and approval processes | POC runbook and operating procedures / Platform operations |
| Technology implementation | Build landing-zone workload components, private OKE clusters, node pools, external services, and integration | Infrastructure-as-code, diagrams, configuration and version matrix / OCI and Kubernetes architects |
| Management and operations | Measure health, performance, cost, capacity, patching, alarms, supportability, and handoff | Dashboards, alarms, cost report, support model, lessons learned / Cloud operations |

## 6.1 CAF stage gates

- Gate 0 - Charter: approve the decision questions, POC funding ceiling, roles, and evidence required.

- Gate 1 - Ready: written vendor prerequisites, OCI capacity, security/network design, and the version matrix are complete.

- Gate 2 - Build: infrastructure-as-code deploys the two POC clusters and their external services without uncontrolled exceptions.

- Gate 3 - Validate: functional, performance, integration, security, resilience, operations, and cost tests complete.

- Gate 4 - Decide: leadership issues Go, Conditional Go, Extend, or No-Go with documented rationale.

# 7. OCI Well-Architected Framework review

Oracle's current WAF is organized around five business goals: security and compliance, reliability and resilience, performance and cost optimization, operational efficiency, and distributed cloud [S2]. The POC must produce evidence for each pillar.

| WAF pillar | POC design and tests | Pass condition |
| --- | --- | --- |
| Security and compliance | Private API/workers, NSGs, IAM/RBAC, service accounts, Vault, encryption, registry scanning, Kubernetes audit logs, egress controls, vulnerability scans | No unapproved public endpoint or critical finding; all required exceptions documented and accepted |
| Reliability and resilience | Health probes, restart, drain, node-loss behavior, fault-domain placement, backup/restore, recovery procedure, service limits | Agreed recovery tests pass and production HA gaps are quantified |
| Performance and cost optimization | CPU, memory, GPU, storage IOPS/latency, network, throughput, concurrency, idle time, and cost per workload | Workload targets met with documented headroom and right-sized target shapes |
| Operational efficiency | IaC, deployment repeatability, logs, metrics, alarms, patch/upgrade/rollback, runbooks, incident and vendor escalation | A second operator can execute the runbook and demonstrate monitoring and rollback |
| Distributed cloud | FastConnect/DRG path, on-premises data sources, DNS, shared integration interface, sovereignty, and migration coexistence | Private hybrid data flows meet security, latency, support, and operational requirements |

## 7.1 Well-Architected design controls

- Resource isolation: separate clusters, node pools, namespaces, service accounts, keys, databases, storage, backups, and ingress per application environment.

- Metrics-driven sizing: do not reproduce the legacy 20-server count one-for-one. Measure node and pod utilization, queue depth, storage behavior, and workload completion [S2].

- GPU scheduling: taint/label the A10 pool, require explicit nvidia.com/gpu requests, and confirm the selected OKE GPU image and vendor driver/CUDA matrix [S7].

- Failure isolation: the two GPUs in one A10.2 VM do not provide node-level high availability; production HA requires a separately approved multi-node pattern.

- Observability: enable OKE metrics, alarms, notifications, Kubernetes API audit logs, application logs, and GPU telemetry [S9].

- Hybrid design: treat FastConnect/DRG routes, DNS, firewall policy, bandwidth, and shared data exchange as tested components of the workload, not external assumptions.

# 8. Technical POC design

## 8.1 DataWalk POC cluster

| Component | POC position |
| --- | --- |
| Cluster | Private, dedicated DataWalk OKE cluster in the non-production boundary |
| System pool | CPU nodes for ingress, DNS/networking, operators, CSI, metrics, and required platform services |
| Application pool | Dedicated CPU workers; OCPU, memory, node count, and storage are frozen only after DataWalk's written sizing response |
| GPU | Not provisioned for DataWalk unless the vendor identifies a supported GPU component and exact software stack |
| State | External DataWalk database and Decoupled Storage pattern as approved by DataWalk |
| OS/image gate | DataWalk publicly identifies RHEL 8.10 or Rocky 8 for the container transition [S10]; vendor must approve the selected managed OKE image or require an alternate platform |

## 8.2 Hyperscience POC cluster

| Component | POC position |
| --- | --- |
| Cluster | Private, dedicated Hyperscience OKE cluster in the non-production boundary |
| CPU platform pool | At least the vendor-approved platform-node count; current planning baseline is 2+ nodes |
| GPU pool | One VM.GPU.A10.2 node for POC unless vendor sizing requires otherwise; two separate NVIDIA A10 24 GB devices |
| Scheduling | Dedicated labels/taints and explicit GPU resource requests; platform pods remain on CPU workers |
| External services | Vendor-supported SQL database, file/object storage, internal registry, ingress, certificates, and secrets |
| Version gate | Hyperscience release, Kubernetes minor, HyperOperator/chart, CUDA, driver, GPU use case, and database/storage versions must be signed before installation [S11] |

## 8.3 Shared integration boundary

The applications remain operationally isolated. If approved, Hyperscience writes authorized output to a controlled integration bucket or file endpoint, and DataWalk reads only the required objects. OCI Object Storage may expose an S3-compatible interface, but interface similarity is not vendor certification. The POC must prove authentication, encryption, object naming, event/queue behavior, checksum, duplicate handling, retention, malware scanning, and error recovery.

# 9. Work plan and deliverables

| Phase | Activities | Exit deliverable |
| --- | --- | --- |
| 0. Mobilize | Approve charter, funding ceiling, owners, test data, vendor participation, data handling, and decision scorecard | Signed POC charter |
| 1. Validate | Freeze application/Kubernetes/OS/image/driver/CUDA/database/storage/registry matrix; confirm A10.2 capacity and service limits | Signed compatibility and capacity matrix |
| 2. Prepare landing zone | Assess compartments, IAM, network, DNS, logging, Vault, budgets/tags, security zones/guardrails, quotas, and jump-host path | Landing-zone readiness checklist |
| 3. Build platform | Deploy two private OKE clusters, CPU/GPU pools, ingress, registry, storage, secrets, monitoring, and alarms using IaC | Repeatable platform build and configuration record |
| 4. Install applications | Vendor-led DataWalk and Hyperscience installation, smoke tests, integration setup, and support-bundle verification | Application installation acceptance |
| 5. Execute tests | Functional, performance, integration, security, resilience, backup/restore, operability, and cost tests | Evidence package and defect log |
| 6. Decide and hand off | Score results, quantify gaps and TCO, document target sizing, lessons, conditions, and implementation plan | POC final report and decision memorandum |

# 10. Test and acceptance plan

Numeric workload thresholds must be agreed before test execution. The POC team may refine test mechanics during build, but it must not lower acceptance thresholds after results are known.

| Test domain | Minimum test | Required evidence | Acceptance |
| --- | --- | --- | --- |
| Platform | Create clusters/pools; verify private endpoints; validate Kubernetes and GPU resources | IaC output, configurations, screenshots/logs | Expected resources healthy; no public worker/API exposure |
| DataWalk function | Ingest representative data; build/query graph; execute integration and management workflows | Test cases, logs, result checksums | 100% critical use cases pass; no unresolved Sev-1/Sev-2 defect |
| Hyperscience function | Process agreed document set; train/infer approved model; export outputs | Accuracy, throughput, job logs, GPU telemetry | Functional and quality thresholds agreed with the application owner are met |
| Integration | HS output to approved endpoint; DW idempotent ingestion; retry and bad-object handling | Object/event logs, checksums, reconciliation | No data loss, silent duplication, or unauthorized access |
| Performance | Baseline and peak workload runs with warm/cold conditions | Latency, throughput, concurrency, CPU/RAM/GPU/IO/network data | Meets frozen target with documented capacity headroom |
| Resilience | Pod restart, cordon/drain, CPU node loss, GPU node outage observation, backup/restore | Timeline, alerts, recovery data | Approved RPO/RTO met or production remediation explicitly costed |
| Security | IAM/RBAC, NSG, egress, image/vulnerability scan, encryption, audit and log forwarding | Control checklist, scan reports, audit events | No critical open finding; exceptions accepted by security |
| Operations | Alarm, incident, patch/upgrade/rollback, support bundle, vendor escalation | Runbook execution and operator sign-off | Named operations team accepts the support model |
| Cost | Tag POC resources; record hourly/daily consumption and idle utilization | Cost report and production model | Complete assumptions and approved budget/TCO range |

## 10.1 Workload definition form

| Measure | DataWalk | Hyperscience |
| --- | --- | --- |
| Dataset/document set | TBD before Gate 1 | TBD before Gate 1 |
| Volume and duration | TBD | TBD |
| Concurrent users/jobs | TBD | TBD |
| Throughput target | TBD | TBD |
| Latency target | TBD | TBD |
| Accuracy/quality target | Not applicable or owner-defined | TBD against current approved baseline |
| RPO/RTO | TBD with security/operations | TBD with security/operations |

# 11. Security, compliance, and ATO evidence

Oracle's SCCA landing-zone guidance describes a standardized framework for DOD mission workloads and IL2/4/5 security baselines [S4]. The existing landing zone remains the control foundation, but application authorization is not inherited automatically. The POC must generate application-specific evidence and document every deviation.

| Control area | POC requirement |
| --- | --- |
| Identity and privileged access | Federated identity/MFA, least-privilege OCI IAM, Kubernetes RBAC, separate service accounts, break-glass process, access review evidence |
| Network | Private cluster endpoints and workers; approved FastConnect/DRG routes; NSGs; firewall/port matrix; controlled ingress/egress; DNS and TLS ownership |
| Data protection | Encryption in transit and at rest; approved OCI Vault keys; separate POC data; backup encryption; retention and disposal procedure |
| Workload security | Signed/scanned images, OCIR controls, non-root/restricted contexts where supported, admission policy, secrets management, documented vendor exceptions |
| Monitoring and audit | OCI Audit, Logging, OKE API audit logs, application/security logs, alarms, time synchronization, retention, and SIEM/CrowdStrike integration as required |
| Vulnerability and configuration | Host/image/container scanning, patch baseline, configuration drift detection, remediation workflow, and evidence hashes |
| Continuity | Backup/restore proof, recovery steps, dependency mapping, and preliminary production DR/RPO/RTO design |

AUTHORIZATION BOUNDARY A successful POC supports the production ATO package; it does not itself authorize production processing or migration.

# 12. Operating model and ownership

| Capability | Accountable role | POC responsibility |
| --- | --- | --- |
| Program decision and funding | Government program sponsor | Approve charter, success criteria, funding ceiling, and final decision |
| POC coordination | Project manager | Schedule prerequisites, vendor sessions, decisions, risks, evidence, and exit review |
| OCI architecture | OCI architecture lead | Landing-zone fit, compartments, network, services, capacity, cost model, and architecture record |
| Kubernetes platform | Kubernetes SME / platform owner | OKE build, node pools, add-ons, policies, upgrades, monitoring, and knowledge transfer |
| DataWalk | DataWalk vendor + application owner | Supported design, installation, test cases, sizing, acceptance, and support statement |
| Hyperscience | Hyperscience vendor + application owner | Supported design, installation, GPU/version matrix, test cases, acceptance, and support statement |
| Security and ATO | Security/ISSO/AO stakeholders | Control review, evidence requirements, findings, exceptions, and production authorization path |
| Network and enterprise access | Network team | FastConnect/DRG routes, firewall policy, DNS, load-balancer reachability, and jump-host access |
| Cloud operations | Operations owner | Monitoring, alerting, patching, backup, incident response, first-response support, and handoff acceptance |

# 13. Schedule and readiness dependencies

Recommended planning baseline: complete prerequisites first, then run approximately 30 execution days (about six calendar weeks) for build, installation, testing, remediation, and decision. Vendor availability, security approvals, capacity, and data preparation can extend the calendar.

| Window | Milestone | Dependency |
| --- | --- | --- |
| Pre-POC, 2-4 weeks | Charter, vendor matrix, A10 capacity, test data, security/network design, accounts and procurement path | All Gate 1 blockers closed |
| Execution days 1-5 | Landing-zone workload preparation and two-cluster build | IaC, quotas, routing, DNS, IAM, keys, registry |
| Days 6-12 | Vendor installation and smoke tests | Vendor engineers and approved artifacts available |
| Days 13-22 | Functional, integration and performance testing | Frozen workload definitions and baseline |
| Days 23-27 | Security, resilience, backup/restore and operational tests | Security and operations participation |
| Days 28-30 | Remediation closeout, cost model, findings and decision review | Evidence package complete |

## 13.1 POC start checklist

- Written DataWalk and Hyperscience support statements received.

- Version compatibility matrix approved and immutable for the POC run.

- A10.2 service limits and physical capacity confirmed in the target OCI Government region.

- OCI budget, tags, compartment placement, quotas, and cost alerts approved.

- FastConnect/DRG routing, firewall ports, DNS, certificates, and jump-host access ready.

- Test data approved, sanitized as required, staged, and accompanied by expected results.

- Security controls, vulnerability thresholds, evidence formats, retention, and exception process agreed.

- Kubernetes SME and both vendor engineers scheduled for build and test windows.

- Rollback/cleanup plan and data-disposal owner approved.

# 14. Risk register

| Risk | Impact | Mitigation / decision trigger |
| --- | --- | --- |
| Managed OKE image not supported by DataWalk | Architecture redesign or self-managed Kubernetes | Obtain written OS/image approval before build; stop at Gate 1 if unresolved |
| A10.2 unavailable or quota-limited | POC delay | Confirm physical capacity and limits; evaluate reservation or approved alternate shape |
| One A10 node mistaken for HA | GPU workload outage during node maintenance/failure | Treat single node as POC only; cost and test 2+ node production option |
| Decoupled Storage interface unsupported | DataWalk 5.2 migration blocked | Vendor-certified interface test; do not infer support from S3 compatibility |
| Hyperscience version/driver/CUDA mismatch | Install or GPU failure | Signed version matrix and vendor-led installation |
| Security exceptions discovered late | ATO delay or rejected production design | Review pod security, egress, FIPS, SELinux, privileges, and scanning before installation |
| POC workload too small or unrepresentative | False performance/cost conclusion | Application owners approve dataset, concurrency, duration, and baseline before test |
| Kubernetes operations gap | Unsustainable production service | Assign SME, complete runbooks and operator demonstration before Go |
| Incomplete TCO | Funding surprise | Include all CPU/GPU nodes, databases, storage, network, licenses, support, security tooling, DR, and labor |
| Contract/renewal delay | Procurement cannot follow POC | Track separately; do not let a favorable POC imply funds or contract authority |

# 15. Cost-management approach

The earlier $132,000 annual / $663,000 five-year figure appears to be a preliminary A10 compute estimate. It is not the complete five-environment solution cost and should remain labeled as such until the target topology is sized.

- Tag every POC resource by application, environment, owner, cost center, and expiration date; apply budgets and alerts through the landing-zone governance model [S3].

- Capture hourly and daily POC cost by service, including stopped-but-billable resources such as storage, load balancers, databases, logging, backups, and reserved capacity.

- Model target-state CPU system pools, DataWalk CPU pools, Hyperscience CPU pools, A10 GPU pools, HA capacity, external databases, storage, registry, monitoring, network, DR, support, licenses, and Kubernetes labor.

- Use measured utilization to right-size; do not map 16 DataWalk and four Hyperscience legacy servers one-for-one to Kubernetes nodes.

- Present low, expected, and high production run-rate scenarios with assumptions and capacity headroom.

# 16. Exit decision and deliverables

| Decision | Use when | Required disposition |
| --- | --- | --- |
| GO | All mandatory gates pass and residual risks are accepted | Authorize implementation planning/procurement for the five-cluster target |
| CONDITIONAL GO | Core feasibility passes but bounded remediations remain | Assign owners, funds, due dates, and a pre-production verification gate |
| EXTEND | Evidence is incomplete but the remaining question is testable | Approve narrow extension with cost cap and exact missing evidence |
| NO-GO | Vendor support, security, performance, operability, integration, or cost is unacceptable | Close POC, preserve evidence, clean resources/data, and pursue alternate design |

## 16.1 Mandatory closeout package

- Executive POC result and decision scorecard.

- Final architecture and architecture decision records.

- Signed vendor compatibility/support matrix.

- Infrastructure-as-code and configuration baseline.

- Test plan, raw evidence, results, defects, remediations, and acceptance signatures.

- Security/ATO evidence index, findings, exceptions, and production control plan.

- Measured cost report and complete target-state TCO assumptions.

- Operations runbooks, monitoring/alert inventory, support escalation, training, and ownership acceptance.

- Implementation roadmap for DW Dev/Test/Prod and HS Dev/Prod, or documented alternate recommendation.

- POC cleanup/data-destruction attestation when applicable.

RECOMMENDED APPROVAL LANGUAGE Approve prerequisite work and a controlled OCI proof of concept using separate DataWalk and Hyperscience non-production OKE clusters. Production authorization remains conditional on written vendor support, successful test evidence, security and ATO review, operational acceptance, confirmed regional capacity, and an approved complete cost model.

# Appendix A. Version and support matrix

| Layer | DataWalk POC | Hyperscience POC | Approval evidence |
| --- | --- | --- | --- |
| Application release | TBD | TBD | Vendor support statement |
| Kubernetes minor | TBD | TBD | Vendor + Oracle support overlap |
| Deployment artifact | Chart/operator TBD | HyperOperator/chart TBD | Signed hash/version |
| Worker image / OS | TBD | TBD | Vendor approval of exact image |
| Kernel/runtime | TBD | TBD | Support matrix |
| NVIDIA driver | Not applicable unless GPU approved | TBD | Vendor-approved version |
| CUDA runtime | Not applicable unless GPU approved | TBD | Vendor-approved version |
| Database | TBD | TBD | Engine/version/privileges |
| Storage | Decoupled Storage TBD | File/object storage TBD | Certified interface and version |
| Registry | OCIR pending approval | OCIR pending approval | Registry API and sync test |
| Ingress/TLS | Private LB/Ingress TBD | Private LB/Ingress TBD | Vendor and security approval |
| Support owner | TBD | TBD | Named escalation path |

# Appendix B. Authoritative sources

Sources were checked on September 3, 2026. Vendor requirements remain release-specific and must be reconfirmed for the selected POC versions.

[S1] Oracle Cloud Infrastructure Cloud Adoption Framework - Defines the six CAF pillars and iterative adoption approach.

[S2] Well-Architected Framework for Oracle Cloud Infrastructure - Defines OCI's five Well-Architected pillars and associated focus areas.

[S3] OCI Landing Zones Overview - Describes Terraform-based landing-zone modules for IAM, networking, security, observability, governance, and workloads.

[S4] OCI Secure Cloud Computing Architecture Landing Zone - Describes the OCI SCCA framework for DOD mission workloads and IL2/4/5 baselines.

[S5] Oracle Kubernetes Engine (OKE) - OKE service documentation and platform entry point.

[S6] OKE Supported Images and Shapes - Defines the supported managed-node image and shape boundary.

[S7] Running Applications on GPU-Based OKE Nodes - Explains GPU managed node pools and compatible GPU images.

[S8] OCI Compute Shapes - Authoritative shape specifications, including NVIDIA A10 GPU characteristics.

[S9] Kubernetes Engine Metrics - Covers OKE health, capacity, performance metrics, alarms, and notifications.

[S10] DataWalk - Preparing for DataWalk on Containers - States the container/Decoupled Storage transition and published RHEL/Rocky requirements.

[S11] Hyperscience Kubernetes Installation Overview - Covers Kubernetes installation, GPU use cases, A10 support, CUDA/driver, and node requirements.

[S12] Hyperscience Infrastructure Requirements - Provides release-specific CPU, RAM, storage, database, GPU, driver, and container requirements.