# OCI to Azure POC Migration Plan and Timeline

DataWalk and Hyperscience

21 September 2026  |  Proposal for review

We propose relocating the planned DataWalk and Hyperscience proof of concept from Oracle Cloud Infrastructure to Azure Government. The POC will preserve separate application clusters, private enterprise connectivity and controlled document exchange. The recommended approach is a clean Azure build followed by application installation and test-data loading, rather than a direct migration of partially built OCI virtual machines.

Target completion: 13 November 2026. Management contingency: 4 December 2026.

The target date assumes an approved Azure Government subscription, existing private connectivity, available GPU capacity and quota, and written vendor confirmation during the first week.

# Decision and Scope

| Area | POC decision |
| --- | --- |
| Cloud | Azure Government in an approved region and subscription. |
| DataWalk | One Dev-equivalent environment on a dedicated three-node CPU VM and Kubernetes cluster. DataWalk does not share workers with Hyperscience. |
| Hyperscience | One Dev-equivalent environment on separate GPU VM and Kubernetes capacity. CPU platform roles remain separate when required by the vendor. |
| Data | Approved representative test data only. Production migration and cutover remain outside this POC. |
| Connectivity | Private access through the enterprise hub and ExpressRoute. Administration uses the approved on-premises Windows jump host. |
| Outcome | A documented proceed, remediate and retest, or stop recommendation based on supportability, security, performance, recovery and cost evidence. |

# Azure Planning Basis

| Component | Proposed Azure implementation |
| --- | --- |
| DataWalk compute | Standard_E16as_v5 is the initial sizing candidate for each worker because it provides 16 vCPUs and 128 GiB memory. Final worker count, disk IOPS and throughput require DataWalk approval. |
| Hyperscience GPU | Standard_NV72ads_A10_v5 is the closest candidate by GPU count to OCI VM.GPU.A10.2 because it provides two NVIDIA A10 GPUs. Validate Azure Government availability, quota, CUDA and driver compatibility, and Hyperscience support before deployment. |
| Operating system | RHEL 8.10 x86-64 is the planning assumption for self-managed Kubernetes VMs. Each vendor must approve the exact OS and Kubernetes release. Managed AKS requires a separately supported node image decision. |
| Network | Dedicated application spoke VNets connected to the enterprise hub. Use NSGs, user-defined routes, private DNS and enterprise firewall inspection. Do not assign public IP addresses to application VMs. |
| Application entry | Private HTTPS through an internal load balancer or approved private application gateway. |
| Platform services | Azure Container Registry, Key Vault, Azure Monitor, Log Analytics, Managed Disks and a supported database service or database VM. |
| Document handoff | Use a dedicated Azure Blob Storage account or another vendor-supported interface. This storage is a controlled exchange point, not shared application storage. |

The OCI A10.2 name cannot be retained in Azure because it is an OCI VM shape. The Azure POC must select an Azure A10 SKU that meets the same functional requirement and is available in the approved government region.

# OCI to Azure Terminology Crosswalk

Use the Azure term when describing the target design. The entries marked as approximate require a design decision because the OCI and Azure services do not have identical boundaries or behavior.

## Organization and Networking

| OCI term | Azure term | POC interpretation |
| --- | --- | --- |
| Tenancy | Microsoft Entra tenant plus Azure hierarchy | Approximate. Identity, billing and resource governance are separated across the tenant, management groups and subscriptions. |
| Compartment | Subscription or resource group | Approximate. Use subscriptions for strong environment or policy boundaries and resource groups for lifecycle grouping. |
| Virtual Cloud Network (VCN) | Virtual Network (VNet) | Private network boundary for application subnets. |
| Dynamic Routing Gateway (DRG) | ExpressRoute virtual network gateway or Virtual WAN hub | Approximate. Select the Azure routing construct that connects the hub, spokes and enterprise network. |
| FastConnect | ExpressRoute | Private provider-based connection between the enterprise network and the cloud. |
| Local or remote VCN peering | VNet peering or global VNet peering | Private routing between Azure virtual networks. |
| Service Gateway | Private Link/private endpoint or service endpoint | Approximate. Prefer private endpoints when the Azure service supports them. |
| NAT Gateway | Azure NAT Gateway | Controlled outbound internet connectivity for private subnets; it does not provide inbound access. |
| Security List / Network Security Group | Network Security Group (NSG) | Filter traffic at Azure subnet or network-interface scope. |
| Route table / route rule | Route table / user-defined route (UDR) | Direct spoke traffic through the enterprise firewall, gateway or approved next hop. |
| OCI Bastion | Azure Bastion | Optional interactive administration service; routine POC access remains through the approved enterprise jump host. |
| OCI Load Balancer | Azure Load Balancer or Application Gateway | Use Load Balancer for Layer 4 traffic and Application Gateway for Layer 7 HTTPS and WAF features. |

## Compute, Kubernetes and Data

| OCI term | Azure term | POC interpretation |
| --- | --- | --- |
| Oracle Kubernetes Engine (OKE) | Azure Kubernetes Service (AKS) | Managed Kubernetes equivalent. The current POC may use self-managed Kubernetes when vendor OS requirements prevent AKS. |
| Compute instance / shape | Virtual machine / VM size | Azure sizes are selected by CPU, memory, disk, network and accelerator requirements; shape names do not translate directly. |
| VM.Standard.E6.Flex | E-series AMD VM candidate | Approximate. Standard_E16as_v5 is the initial DataWalk candidate for 16 vCPUs and 128 GiB memory. |
| VM.GPU.A10.2 | Standard_NV72ads_A10_v5 candidate | Approximate. Both expose two NVIDIA A10 GPUs, but quota, regional availability, drivers and vendor support must be validated. |
| Block Volume | Azure Managed Disks | Persistent operating-system and application block storage. |
| File Storage | Azure Files or Azure NetApp Files | Managed shared file storage; choose the service only after protocol and performance validation. |
| Object Storage | Azure Blob Storage | Candidate controlled exchange point for Hyperscience output and DataWalk ingestion. |
| Oracle Cloud Infrastructure Registry (OCIR) | Azure Container Registry (ACR) | Private registry for application and platform container images. |

## Identity, Security and Operations

| OCI term | Azure term | POC interpretation |
| --- | --- | --- |
| Identity domain / IAM | Microsoft Entra ID | Workforce and workload identity foundation. |
| IAM policy | Azure RBAC plus Azure Policy | Approximate. RBAC grants access; Azure Policy enforces or audits resource configuration. |
| Vault | Azure Key Vault | Store secrets, keys and certificates outside application configuration. |
| Cloud Guard | Microsoft Defender for Cloud | Cloud security posture, recommendations and workload protection capabilities. |
| Security Zones | Azure Policy initiatives and landing-zone guardrails | Approximate. Enforce approved configurations at management-group, subscription or resource-group scope. |
| Logging / Monitoring | Azure Monitor and Log Analytics | Central platform metrics, logs, queries, dashboards and alerts. |
| VCN Flow Logs | Virtual Network Flow Logs | Network-flow evidence for troubleshooting and security analysis. |
| Resource Manager (ORM) | Azure Resource Manager/Bicep or Terraform pipeline | No exact managed-Terraform equivalent. This POC will use Terraform with an approved delivery pipeline. |

# Migration Workstreams

| Workstream | Required work | Completion evidence |
| --- | --- | --- |
| Governance | Confirm subscription, region, funding, permitted data classification, resource owners, tags and deletion date. | Approved scope, budget and ownership record. |
| Vendor validation | Confirm application releases, OS, Kubernetes, CPU and GPU topology, database, storage protocol and installation support. | Written DataWalk and Hyperscience compatibility decisions. |
| Platform engineering | Translate OCI Terraform into Azure Terraform using the azurerm provider. Build the hub-connected spokes and shared platform services. | Reviewed Terraform plan and deployment record. |
| Security and identity | Apply Azure Policy, RBAC, Key Vault, logging, vulnerability scanning, NSGs, firewall rules and private administration paths. | Security checklist, access tests and log samples. |
| Application deployment | Build separate clusters, install DataWalk and Hyperscience, load licenses, configure dependencies and complete smoke tests. | Vendor-confirmed healthy installations. |
| Data and integration | Load approved test data and reproduce the Hyperscience output, postprocessing and DataWalk ingestion workflow. | Reconciled input and output manifest. |
| Testing and decision | Measure functionality, performance, accuracy, recovery, security findings, operating effort and Azure cost. | Signed POC results and recommendation. |

# Eight Week Timeline

| Wk | Dates | Activities | Exit criterion |
| --- | --- | --- | --- |
| 1 | Sep 21–25 | Confirm Azure Government region and subscription. Validate vendor support, RHEL and Kubernetes versions, VM sizing, A10 quota and capacity. Freeze additional OCI POC build work. | Architecture decisions, capacity path and owners approved. |
| 2 | Sep 28–Oct 2 | Complete detailed design, IP plan, resource hierarchy, DNS, routes, firewall flows, storage interfaces, security controls, test dataset and acceptance targets. | Detailed design and POC test plan approved. |
| 3 | Oct 5–9 | Deploy the Azure foundation with Terraform: resource groups, spoke VNets, hub connection, private DNS, NSGs, routes, Key Vault, ACR, Log Analytics and budgets. | Private foundation is reachable from the approved jump host. |
| 4 | Oct 12–16 | Build the dedicated DataWalk CPU cluster. Configure RHEL, Kubernetes, persistent disks, access controls, monitoring and backup jobs. | DataWalk platform health and storage persistence tests pass. |
| 5 | Oct 19–23 | Build the separate Hyperscience GPU cluster. Install approved NVIDIA drivers and CUDA dependencies. Validate GPU count, memory, scheduling and storage. | Vendor-approved GPU validation passes. |
| 6 | Oct 26–30 | Install both applications. Configure databases, registry access, secrets, certificates, private ingress and document handoff. Complete smoke tests. | Both applications and a sample handoff operate successfully. |
| 7 | Nov 2–6 | Run functional, integration, performance, accuracy, backup, restore, monitoring and cost tests using the approved dataset and baselines. | Test evidence is complete; failures have owners and dispositions. |
| 8 | Nov 9–13 | Complete security review and user acceptance. Resolve agreed priority findings. Prepare the as-built design, measured cost, production considerations and final recommendation. | Sponsor records the POC decision. |

# Milestones and ETA

| Milestone | Planned date |
| --- | --- |
| Vendor and capacity decisions complete | 25 September 2026 |
| Azure foundation ready | 9 October 2026 |
| DataWalk cluster ready | 16 October 2026 |
| Hyperscience GPU cluster ready | 23 October 2026 |
| Applications installed | 30 October 2026 |
| Technical testing complete | 6 November 2026 |
| POC recommendation complete | 13 November 2026 |
| Management contingency date | 4 December 2026 |

# POC Acceptance Criteria

DataWalk runs on its dedicated Azure CPU cluster and does not share workers, storage, secrets, database, ingress or upgrade lifecycle with Hyperscience.

Hyperscience runs on its dedicated Azure GPU infrastructure, and the selected workload can see and use the approved NVIDIA A10 capacity.

Administrators reach both environments privately from the approved jump host through ExpressRoute and the enterprise security inspection path.

Users reach private HTTPS application endpoints without public application IP addresses.

Hyperscience processes the representative document set and meets the accuracy target agreed before testing.

The controlled handoff delivers expected Hyperscience output to DataWalk without unexplained missing documents or duplicate records.

DataWalk ingestion and representative queries produce the expected results within the approved performance tolerance.

Application-consistent backup and restore tests complete within the agreed recovery target.

Required logs reach Azure Monitor and Log Analytics, and the named responder receives a test alert.

No unresolved critical or high security finding remains without an approved POC disposition.

Actual consumption stays within the approved POC budget, and the final report separates measured POC cost from the production forecast.

# Responsibilities

| Role | Primary responsibility |
| --- | --- |
| Project manager | Maintain schedule, dependencies, decisions, risks, vendor sessions and acceptance evidence. |
| Azure engineering | Design and deploy the Azure foundation, compute, storage, monitoring and Terraform. |
| Network and security | Approve routing, firewall rules, DNS, access controls, logging and security findings. |
| Kubernetes engineer | Build, secure and operate the separate DataWalk and Hyperscience clusters. |
| DataWalk team | Approve sizing and platform support; install and validate DataWalk. |
| Hyperscience team | Approve GPU, driver, CUDA and platform support; install and validate Hyperscience. |
| Application owners | Provide test data, baselines, integration behavior and user acceptance. |
| Sponsor and budget owner | Approve scope, funding, exceptions and the final POC recommendation. |

# Schedule Risks and Decision Gates

| Risk or gate | Potential impact | Required response |
| --- | --- | --- |
| A10 SKU unavailable or quota denied | Two to six weeks | Confirm capacity and submit quota requests during Week 1. Do not substitute another GPU without Hyperscience approval. |
| New ExpressRoute connection required | Four to eight weeks or more | Use the existing enterprise connection when available. Rebaseline the schedule if a new circuit is required. |
| Vendor does not approve the selected OS, Kubernetes release or Azure SKU | One to three weeks | Obtain written decisions before infrastructure deployment and price the supported alternative. |
| Security authorization requires additional controls | Two to four weeks | Start the security review in Week 1 and track each control owner and evidence item. |
| Vendor engineering resources are unavailable | One to three weeks | Reserve installation and troubleshooting windows before Week 4. |

Schedule decision: retain 13 November 2026 as the target only when the Week 1 gates pass. Use 4 December 2026 as the management commitment date when ordinary remediation or scheduling contingency is needed. If a new ExpressRoute circuit or unavailable government-region GPU capacity is encountered, replan the effort as a 12- to 16-week project.

# Closeout Deliverables

The closeout package will include the approved scope; detailed and as-built Azure designs; Terraform and deployment evidence; vendor decisions; test results; security dispositions; measured cost; production estimate; and final recommendation. Remove temporary OCI POC resources only after the evidence is preserved and decommissioning is authorized.

# References

Azure landing zones

Azure Well Architected Framework

NVadsA10 v5 virtual machine specifications

Azure ExpressRoute overview

OCI FastConnect overview

Azure networking services overview